## oer
Tasks | Assigned To | Start Date | End Date | Priority | Status | EST HOURS | ACTUAL HOURS | BUDGET | Notes
Requirement Specifications
Design backend architecture | moses omondi |  |  | HIGH
Identify Operating System(OS) | moses omondi | 2022-03-06 | 2022-03-08 | LOW | Complete
Allocate ram, hard-drive and networking resources | moses omondi | 2022-03-06 | 2022-03-13 | LOW | Complete
Update OS | moses omondi |  |  | LOW | Complete
Test Network Connection and assigned ports | moses omondi |  |  | LOW | Complete
Install postgre database,elastic search,redis ,pgsync , nginx and mongo db | moses omondi |  |  | HIGH | Complete
Acquire Data
Identify data sources |  |  |  | HIGH
x5gon | muoki caleb |  |  |  | Complete
Open Library | moses omondi |  |  |  | Complete
Teacher Future | moses omondi |  |  |  | Complete
Semantic Scholar | moses omondi |  |  |  | Complete
Validate Data |  |  |  | HIGH
x5gon | muoki caleb |  |  |  | Complete
Open Library | moses omondi |  |  |  | Complete
Teacher Future | moses omondi |  |  |  | Complete
Semantic Scholar | moses omondi |  |  |  | Complete
Download data |  |  |  | HIGH
x5gon | muoki caleb |  |  |  | Complete
Open Library | moses omondi |  |  |  | Complete
Teacher Future | moses omondi |  |  |  | Complete
Semantic Scholar | moses omondi |  |  |  | Complete
Backup Unstructured data | moses omondi |  |  |  | Complete
Clean Data
Extract Data | moses omondi |  |  | HIGH | Complete
Prepare data cleaning scripts | moses omondi |  |  | HIGH | Complete
Examine data quality | moses omondi |  |  | HIGH | Complete
Teacher Future |  |  |  |  | In Progress |  |  |  | Documents presented in formats not suitable for automated topic modeling and keyword extraction. Tedious manual work of reading documents and listening to media files .Key metric construction.
Remove noise from data | moses omondi |  |  |  | Complete
Export Structured data to various containers i.e csv | moses omondi |  |  |  | Complete
Store Structured Data
Prepare necessary databases and relations | moses omondi |  |  | HIGH | Complete
create appropriate scripts for exporting data to db and testing exported data | moses omondi |  |  | HIGH | Complete
export csv data to db | moses omondi |  |  | HIGH | Complete
Data Syncing
Configure and Intergrate syncing pipeline | moses omondi |  |  | HIGH | Complete
Postgresql
Elastic search
Redis
Pgsync
.env
schema.json
Bootstrap syncing script | moses omondi |  |  | HIGH | Complete
schema.json
Index data
Run pgsync command | moses omondi |  |  | HIGH | Complete
Monitor memory and storage usage | moses omondi |  |  | HIGH | Complete
Monitor index progress | moses omondi |  |  | HIGH | Complete
High quality search results based on user query
Generate scripts for querying indexed data via api | moses omondi |  |  | HIGH | Complete
create python script as api endpoint based on various indexes | moses omondi |  |  | HIGH | Complete
install and use postman to reach the python endpoint | moses omondi |  |  | HIGH | Complete
validate quality of results based on key metrics | moses omondi |  |  | HIGH | Complete
Index Score
Topic
Date Created
Abstract
hand in apis to front end and testing | moses omondi |  |  | HIGH | Complete
improve the results based on testing feedback | moses omondi |  |  | HIGH | Complete
AI filtered results |  |  |  |  | In Progress |  |  |  | should be available on recommender
Identify AI model to filter search | moses omondi |  |  | LOW | Complete
Deploy AI model (CPU) | moses omondi |  |  | LOW | Complete
Generate Query Scripts | moses omondi |  |  | LOW | Complete
Test Model on CPU | moses omondi |  |  | LOW | Complete |  |  |  | Good but slow results output
Test Model on GPU | moses omondi |  |  | LOW |  |  |  |  | No GPU environment currently available
Back End System Documentation
Source Code | moses omondi |  |  | HIGH | Complete
Apis | moses omondi |  |  | HIGH | Complete
Database | moses omondi |  |  | MEDIUM | In Progress

## Summary
At Risk | 0
Overdue Tasks | 0
Complete Count | 43
In Progress Count | 3
Not Started Count | 0